## Sheet1
Agile Project Plan
Project Name | Monitoring Pregnancy using Mobile Applications
Project Manager | Xiang ZHANG
Start Date | 2018-10-09
End Date | 2019-05-07
Task Name | Responsible | Start | End | Days | Status
PREPARATORY - Paperwork | Xiang ZHANG | 2018-10-09 | 2018-10-22 | 13 | Complete
Supervisor Agreement From | Xiang ZHANG | 2018-10-09 | 2018-10-12 | 3 | Complete
Detailed Project Proposal | Xiang ZHANG | 2018-10-09 | 2018-10-15 | 6 | Complete
Preliminiary Research Ethic Checklist | Xiang ZHANG | 2018-10-16 | 2018-10-22 | 6 | Complete
Revised Project Proposal | Xiang ZHANG | 2018-10-16 | 2018-10-22 | 6 | Complete
PREPARATORY - Data Analysis | Xiang ZHANG | 2018-10-23 | 2018-12-17 | 55 | In progress
Literature Review | Xiang ZHANG | 2018-10-23 | 2018-11-26 | 34 | In progress
Pregnancy Data Analysis | Xiang ZHANG | 2018-11-06 | 2018-11-26 | 20 | In progress
Machine Learning Plan | Xiang ZHANG | 2018-11-26 | 2018-12-17 | 21 | In progress
PREPARATORY - Structure | Xiang ZHANG | 2018-10-30 | 2018-12-03 | 34 | In progress
Draft of Poster | Xiang ZHANG | 2018-10-30 | 2018-11-05 | 6 | Complete
Revised Poster | Xiang ZHANG | 2018-11-05 | 2018-11-07 | 2 | Complete
Initial Design | Xiang ZHANG | 2018-11-05 | 2018-11-07 | 2 | Complete
Website | Xiang ZHANG | 2018-11-15 | 2018-11-16 | 1 | In progress
Software Project Plan | Xiang ZHANG | 2018-11-15 | 2018-11-28 | 13 | In progress
Detailed Software Design | Xiang ZHANG | 2018-11-26 | 2018-12-03 | 7 | In progress
SOFTWARE DEVELOPMENT - 1 | Xiang ZHANG | 2018-11-20 | 2018-12-11 | 21 | In progress
Data Standardize protocol | Xiang ZHANG | 2018-11-20 | 2018-12-11 | 21 | Not started
SOFTWARE DEVELOPMENT - 2 | Xiang ZHANG | 2018-12-11 | 2019-01-08 | 28 | Not started
User interface | Xiang ZHANG | 2018-12-11 | 2019-01-08 | 28 | Not started
SOFTWARE DEVELOPMENT - 3 | Xiang ZHANG | 2019-01-08 | 2019-03-04 | 55 | Not started
Summary data analytics | Xiang ZHANG | 2019-01-08 | 2019-02-03 | 26 | Not started
Decision-Making | Xiang ZHANG | 2019-02-04 | 2019-03-04 | 28 | Not started
SOFTWARE DEVELOPMENT - 4 | Xiang ZHANG | 2019-03-05 | 2019-04-27 | 53 | Not started
Case study | Xiang ZHANG | 2019-03-05 | 2019-03-19 | 14 | Not started
software Development | Xiang ZHANG | 2019-03-19 | 2019-04-27 | 39 | Not started
REPORTING - 1 | Xiang ZHANG | 2018-10-09 | 2019-04-23 | 196 | In progress
Incremental Progress and Monthly Reports | Xiang ZHANG | 2018-10-09 | 2019-01-07 | 90 | In progress
Demonstration day | Xiang ZHANG | 2019-01-07 | 2019-04-23 | 106 | Not started
REPORTING - 2 | Xiang ZHANG | 2019-01-01 | 2019-01-07 | 6 | Not started
Interim report submission | Xiang ZHANG | 2019-01-01 | 2019-01-07 | 6 | Not started
REPORTING - 3 | Xiang ZHANG | 2018-10-09 | 2019-02-05 | 119 | In progress
Dissertation plan and schedule - 1 | Xiang ZHANG | 2018-11-15 | 2018-11-28 | 13 | In progress
Dissertation plan and schedule - 2 | Xiang ZHANG | 2019-01-08 | 2019-02-05 | 28 | Not started
REPORTING - 4 | Xiang ZHANG | 2018-10-30 | 2019-05-07 | 189 | In progress
Preliminary draft (structure) - 1 | Xiang ZHANG | 2018-10-30 | 2018-11-26 | 27 | Not started
Preliminary draft (structure) - 2 | Xiang ZHANG | 2018-11-21 | 2019-01-08 | 48 | Not started
First draft | Xiang ZHANG | 2019-02-12 | 2019-04-09 | 56 | Not started
Dissertation submission | Xiang ZHANG | 2019-04-29 | 2019-05-06 | 7 | Not started
Demonstration day | Xiang ZHANG | 2019-04-30 | 2019-05-07 | 7 | Not started